## Gantt Chart
Block D — NLP Project Roadmap & Gantt Chart
NLP: English → Dutch Translation + Emotion Classification ¦ Due: 12 June 2026
Task | Category | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
SPRINT 1 — Planning & Setup
GitHub repo, branching strategy, README | Infrastructure | ▶ | ◀
Azure DevOps boards + backlog | Infrastructure | ▶ | ◀
Architecture diagram (initial draft) | Infrastructure | ▶ | ◀
Package plan — module structure & interfaces | Planning | ▶ | ◀
Project roadmap & milestones | Planning | ▶ | ◀
Virtual envs & dependency management | Code | ▶ | ◀
Sprint review + retrospective #1 | Agile |  | █
SPRINT 2 — MVP Inference Application
NLP Python package (transcription + EN→NL + emotions) | Code |  |  | ▶ | ◀
CLI for inference | Code |  |  | ▶ | ◀
Unit tests + logging + error handling | Code |  |  | ▶ | ◀
Sphinx docs + docstrings | Code |  |  | ▶ | ◀
FastAPI inference endpoint (with confidence scores) | API |  |  | ▶ | ◀
Docker containers — backend + frontend + DB | Infrastructure |  |  |  | █
On-premise deployment on Portainer | Deployment |  |  |  | █
Sprint review + retrospective #2 | Agile |  |  |  | █
SPRINT 3 — Data Pipelines & Cloud Training
Azure ML workspace setup | Cloud |  |  |  |  | █
Data upload + versioned data assets | Data |  |  |  |  | █
Cloud environments + test training job | Data |  |  |  |  | ▶ | ◀
Azure ML pipeline (ingest→preprocess→train→eval→register) | Data |  |  |  |  | ▶ | ◀
MLflow experiment tracking + learning curves | Data |  |  |  |  | ▶ | ◀
Hyperparameter tuning pipeline | Data | [5 empty] | █
Scheduled / triggered pipeline | Data | [5 empty] | █
Streamlit / Gradio frontend (containerised + deployed) | Frontend |  |  |  |  | ▶ | ◀
Sprint review + retrospective #3 | Agile | [5 empty] | █
SPRINT 4 — Deployment, Monitoring & Retraining
CI/CD pipeline (GitHub Actions — lint, test, deploy) | Deployment | [5 empty] | ▶ | ◀
Cloud endpoints with model version control | Deployment | [6 empty] | █
Operational monitoring (latency, drift, error rates) | Monitoring | [6 empty] | █
User feedback loop + retraining trigger | Monitoring | [6 empty] | █
Monitoring dashboard (business-insight visualisations) | Frontend | [6 empty] | ▶ | ◀
Sprint review + retrospective #4 | Agile | [6 empty] | █
SPRINT 5 — Testing, Polish & Demo
Synthetic + real-user testing | Testing | [6 empty] | ▶ | ◀
Azure cost analysis | Documentation | [6 empty] | ▶ | ◀
Final README, .whl + source distribution | Code | [7 empty] | █
Demo day preparation (4 screens) | Demo | [7 empty] | █
★ DEADLINE — all deliverables due 12 June | MILESTONE | [7 empty] | ◆
Legend
Sprint 1 — Infrastructure / setup |  | Sprint 2 — Code & packaging |  | Sprint 3 — Data & cloud training
Sprint 4 — Deployment & monitoring |  | Sprint 5 — Testing & demo |  | Milestone

## Sprint Breakdown
Sprint Breakdown — Goals & ILO Mapping
Sprint 1 — Planning & Setup — Weeks 1–2
# | Goal / Task | Category | ILO | Must-Pass?
1 | GitHub repo with branching strategy & protected branches | Infrastructure | ILO 9.5
2 | Package plan — module structure, interfaces, dependencies | Planning | ILO 4.4
3 | Architecture diagram (data, training, deployment) | Planning | ILO 4.4
4 | Project roadmap and product backlog in Azure DevOps | Project Mgmt | ILO 4.4
5 | Virtual environments and dependency management | Code | ILO 9.3
6 | Sprint review + retrospective | Agile | ILO 2.8
Sprint 2 — MVP Inference Application — Weeks 3–4
# | Goal / Task | Category | ILO | Must-Pass?
1 | Python package: transcription → EN→NL → emotion classification | Code | ILO 9.3 | ★ Must-pass
2 | CLI for inference with clear usage examples | Code | ILO 9.3 | ★ Must-pass
3 | Unit tests (target >55%), logging, error handling | Testing | ILO 9.3 | ★ Must-pass
4 | Sphinx docs + comprehensive docstrings | Documentation | ILO 9.3 | ★ Must-pass
5 | FastAPI inference endpoint (video/audio input, confidence scores) | API | ILO 9.5 | ★ Must-pass
6 | Docker containers — backend, frontend, database | Infrastructure | ILO 9.5 | ★ Must-pass
7 | On-premise deployment on Portainer | Deployment | ILO 9.5 | ★ Must-pass
8 | Sprint review + retrospective | Agile | ILO 2.8
Sprint 3 — Data Pipelines & Cloud Training — Weeks 5–6
# | Goal / Task | Category | ILO | Must-Pass?
1 | Upload data to Azure ML, create versioned data assets | Data | ILO 9.4 | ★ Must-pass
2 | Cloud environments + test training job | Cloud | ILO 8.9
3 | Azure ML pipeline: ingest → preprocess → train → eval → register | Pipeline | ILO 8.9 / 9.4 | ★ Must-pass
4 | MLflow experiment tracking + learning curves + example outputs | Tracking | ILO 8.9
5 | Hyperparameter tuning pipeline | Pipeline | ILO 8.9
6 | Scheduled / triggered pipeline (weekly retraining) | Pipeline | ILO 9.4 | ★ Must-pass
7 | Streamlit / Gradio frontend — containerised + deployed | Frontend | ILO 10.3
8 | Sprint review + retrospective | Agile | ILO 2.8
Sprint 4 — Deployment, Monitoring & Retraining — Week 7
# | Goal / Task | Category | ILO | Must-Pass?
1 | CI/CD pipeline — GitHub Actions (lint, test, auto-deploy) | Deployment | ILO 9.5 | ★ Must-pass
2 | Cloud endpoints with model version control | Deployment | ILO 9.5 | ★ Must-pass
3 | Operational monitoring: latency, error rates, drift detection | Monitoring | ILO 9.5 | ★ Must-pass
4 | User feedback loop + triggered retraining pipeline | Retraining | ILO 9.5 | ★ Must-pass
5 | Monitoring dashboard with business-insight visualisations | Frontend | ILO 10.3
6 | Sprint review + retrospective | Agile | ILO 2.8
Sprint 5 — Testing, Polish & Demo — Week 8
# | Goal / Task | Category | ILO | Must-Pass?
1 | Synthetic data + real-user testing evidence | Testing | ILO 9.3 / 9.5 | ★ Must-pass
2 | Azure cloud cost analysis | Documentation | ILO 4.4
3 | Final README, .whl + source distribution | Code | ILO 9.3 | ★ Must-pass
4 | Demo Day — 4 screens: app, docs, poster, evidence | Demo | ILO 10.3
5 | Learning log, work log, peer reviews submitted | Admin | ILO 1.8 / 2.8

## Deliverables & ILOs
Deliverables Checklist — Due Friday 12 June 2026, 16:59
Total deliverables | Must-pass ILOs | Points for ILO 9 | Min. score to pass
17 | 3 (9.3 · 9.4 · 9.5) | 50 / 100 | 55% each must-pass
| Deliverable | ILO(s) | Sprint | Must-Pass
☐ | GitHub repo with all code and documentation | 1.8 / 9.3 / 9.5 | Sprint 1
☐ | README.md — install & usage instructions | 9.3 | Sprint 2 | ★ Must-pass
☐ | Installable Python package (.whl + source dist) | 9.3 | Sprint 2 | ★ Must-pass
☐ | Package plan (modules, interfaces, dependencies) | 4.4 | Sprint 1
☐ | Docker container — training & inference API | 9.5 | Sprint 2 | ★ Must-pass
☐ | Docker container — frontend | 9.5 / 10.3 | Sprint 2 | ★ Must-pass
☐ | Docker container — database | 9.5 | Sprint 2 | ★ Must-pass
☐ | On-premise deployment on Portainer | 9.5 | Sprint 2 | ★ Must-pass
☐ | Azure ML workspace (models, runs, pipelines, endpoints) | 8.9 / 9.4 | Sprint 3 | ★ Must-pass
☐ | Cloud deployment on Azure | 9.5 | Sprint 4 | ★ Must-pass
☐ | Data pipelines — ingestion & preprocessing | 9.4 | Sprint 3 | ★ Must-pass
☐ | Orchestration definitions + schedule/trigger config | 9.4 | Sprint 3 | ★ Must-pass
☐ | Architecture diagrams (data, training, deployment) | 4.4 | Sprint 1
☐ | Azure cloud cost analysis | 4.4 | Sprint 5
☐ | Project plan, roadmap, product & sprint backlog | 4.4 | Sprint 1
☐ | Learning log, work log, peer reviews | 1.8 / 2.8 | Ongoing
☐ | Demo Day — local + on-premise + cloud (4 screens) | 10.3 | Sprint 5